## Sheet1
# | Report date | Reported by | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Actual Results | Expected Results | Steps to reproduce | Assigned To | Notes (Potential fix, close notes)
1 | 2025-02-20 | Matias | P3 | Resolved | Projectiles sometimes go through walls | Projectile stop at wall | Shoot rapidly at wall at ~60 FPS or lower | Matias
2 | 2025-02-21 | Matias | P2 | Resolved | Player projectiles colliding with player | Player’s bullets dont collide with them | Shoot bullet | Matias
3 | 2025-02-22 | Mana | P5 | Resolved | Enemies can see players through walls | Enemies cannot see through walls | Get within enemy detection distance but on the other side of a wall. Enemy will start shooting at player even though line of sight has not been made | Clive
4 | 2025-02-22 | Clive | P4 | Resolved | Player can shoot through walls if they stick the gun up close to a wall and point perpendicular to the wall | Players can't shoot through walls | Get close to a wall and shoot | Clive
5 | 2025-02-23 | Mana | P4 | Resolved | Laser goes through walls | Laser stops at walls | Get close to a wall and face it | Parsa
6 | 2025-02-20 | Parsa | P3 | Resolved | Player can see cursor on top of crosshair | Cursor is hidden | Just play the game and look at the cursor | Matias
7 | 2025-03-08 | Parsa | P4 | Resolved | Particles go off diagonally from the wall | Sometimes, particles go off parallel to the wall | Get close to a wall and shoot | Parsa | collision issue
8 | 2025-03-09 | Matias | P4 | Resolved | When you shoot with your wall in a wall, it casts the shadow as if the gun was fired from inside the wall | The muzzle flash is generated "outside" the wall | Get close to a wall and face it then shoot | Matias
9 | 2025-03-14 | Matias | P2 | In-progress | Camera goes black, game crashes when shooting | Game behaves normally, doesn't crash when we shoot | Place cursor as close as you can to the player center | Matias
10 | 2025-03-21 | Clive | P2 | Resolved | Game unresponsive, unable to open game window | able to open game window after looking at another screen | on my laptop AND when running on power saver mode, open the game, alt tab out of the game, then try to alt tab back into game. game freezes upon alt tabbing back into game | Clive | console behavior not bug.
11 | 2025-03-21 | Clive | P3 | Resolved | Enemies can walk through props | Enemies do not walk through props | make enemy chase you through a prop | clive | Add TILE_ID::WALL or create TILE_ID::PROP and update traversable()
12 | 2025-03-21 | clive | P5 | Resolved | Picking up pistol pickup does not change ammo | Expected. Not implemented | kill enemy then walk over pickup | jeff | Inside collect_pickup() add handle_reload()
13 | 2025-03-23 | Jeff | P5 | won't fix | Health packs render on top of player | Expected. Need to refactor renderring system. | Walk over a health pack. | Matt
14 | 2025-03-25 | Matias | P3 | Resolved | Thrown gun pushes enemy | Should damage enemy | Throw gun at enemy at a distance where the gun will touch the enemy when moving slowly | jeff
15 | 2025-03-25 | Clive | p3 | Resolved | Enemy not rotating while pathfinding to player | enemy should rotate while pathfinding to player | move toward enemy then run away as they start pathfinding towards you | clive | due to enemy lerp movement. bug goes away when reverting
16 | 2025-03-26 | Clive | P3 | Resolved | When on third level, pressing P restarts but gives player a pistol instead of a shotgun | should get a pistol not a shotgun | on third level, press P to restart level | jeff
17 | 2025-03-26 | clive | p2 | Resolved | after shooting a picking up ammo after a while, run out of ammo in gun and unable to reload | should be able to reload | 126 ammo in reserve. picking up ammo does not add to the reserver ammo | jeff
18 | 2025-03-06 | clive | p2 | Resolved | enemies phase through doors | enemies should not be able to move through doors | alert an enemy that is facing you on the other side of the door, then run away | jeff